## Week 36
|  |  | A | B | C | D | E
BL NO | CONTAINER NO | 1st ETA Update | Ship confirm date | Booking date | Port departure date | Port arrival date | WH Delivery date | REMARKS | 提单号（D/R No.) | Invoice Number: | GD/DE | WLE ALE USD | shipconfirm to booking (B-A) | booking to departure (C-B) | voyage days (D-C) | port to WH delivery (E-D) | shipconfirm to wh delivery (E-A)
CNSHA0001407677 | MSNU2800131 | ETA SIN 29 AUG | [5 empty] | schedule delivery 07 SEP, incurs PSA storage & carrier demurrage | 177ISKSKS01743 | UNI-24-R214 | DE
CNSHA0001407687 | MSNU2800194 | ETA SIN 29 AUG | [5 empty] | schedule delivery 03 SEP, incurs PSA storage & carrier demurrage | 177ISKSKS01744 | UNI-24-R215~R218 | DE
CNSHA0001411428 | MSNU2806530 | ETA SIN 29 AUG | [5 empty] | schedule delivery 04 SEP, incurs PSA storage & carrier demurrage | 177ISKSKS01766 | UNI-24-R219~R221 | DE
CNSHA0001411431 | MSNU2793032 | ETA SIN 29 AUG | [5 empty] | schedule delivery 05 SEP, incurs PSA storage & carrier demurrage | 177ISKSKS01767 | UNI-24-R219~R223 | DE
CNSHA0001412866 | MEDU6518896 | ETA SIN 02 SEP | [6 empty] | 177ISKSKS01783 | UNI-24-R225~R232 | DE
CNSHA0001412869 | MSMU2300240 | ETA SIN 02 SEP | 2024-07-12 | 2024-08-07 | 2024-08-26 | 2024-09-04 | 2024-09-10 |  | 177ISKSKS01784 | UNI-24-R233~R237 | GD | 389669.57 | 26 | 19 | 9 | 6 | 60
CNSHA0001414830 | MSNU1237044 | ETA SIN 18 SEP | 2024-08-01 | 2024-08-13 | 2024-09-06 | 2024-09-24 | 2024-09-26 | schedule delivery 24 SEP | 177ISKSKS01797 | UNI-24-R238~242 | GD | 186330.3 | 12 | 24 | 18 | 2 | 56
CNSHA0001414834 | MSNU1236270 | ETA SIN 18 SEP | [5 empty] | schedule delivery 30 SEP | 177ISKSKS01798 | UNI-24-R243~246 | DE | 127953.64
CNSHA0001417580 | FTAU1524342 | ETA SIN 24 SEP | [5 empty] | schedule delivery 26 SEP | 177ISKSKS01836 | UNI-24-R248~252 | DE | 113913.74
CNSHA0001417583 | SEKU1004468 | ETA SIN 24 SEP | [5 empty] | schedule delivery 27 SEP | 177ISKSKS01837 | UNI-24-R253~259 | DE | 143567.27
CNSHA0001420508 | MEDU6772365 | ETA SIN 24 SEP | 2024-08-14 | 2024-08-30 | 2024-09-14 | 2024-09-24 | 2024-09-25 | schedule delivery 25 SEP | 177ISKSKS01855 | UNI-24-R260~265 | GD | 177510.69 | 16 | 15 | 10 | 1 | 42
CNSHA0001420512 | FCIU5809019 | ETA SIN 24 SEP | [5 empty] | schedule delivery 28 SEP | 177ISKSKS01856 | UNI-24-R268~270 | DE | 101891.95
CNSHA0001422834 | MEDU6702497 | ETA SIN 29 SEP | 2024-08-22 | 2024-09-06 | 2024-09-25 | 2024-10-14 | 2024-10-15 |  | 177ISKSKS01877 | UNI-24-R271~275 | GD | 270892.86 | 15 | 19 | 19 | 1 | 54
CNSHA0001422838 | pending pick up container | ETA SIN 29 SEP | [6 empty] | 177ISKSKS01878 | UNI-24-R276~277 | DE | 80159.15
CNSHA0001429228 | MSCU6879655 | ETA SIN 15 OCT | 2024-09-18 | 2024-09-27 | 2024-10-10 | 2024-10-26 | 2024-10-29 |  |  |  | GD | 387733.68 | 9 | 13 | 16 | 3 | 41
CNSHA0001429229 | pending pick up container | ETA SIN 15 OCT |  | 2024-09-27 | 2024-10-05 | 2024-10-16 | 2024-10-18 |  |  |  | DE | 152736.88
CNSHA0001427370 | TCLU2740447 | ETA SIN 30 OCT | [8 empty] | DE
CNSHA0001427373 | MSNU2472011 | ETA SIN 30 OCT | [8 empty] | DE
CNSHA0001432150 | MSDU1694117 | ETA SIN 07 NOV | [8 empty] | DE
CNSHA0001432151 | GLDU3186667 | ETA SIN 07 NOV | [8 empty] | DE
CNSHA0001434107 | MEDU5009390 | ETA SIN 16 NOV | [8 empty] | DE | 104626.8
CNSHA0001434108 | GLDU5492223 | ETA SIN 16 NOV | 2024-10-08 | 2024-10-18 | 2024-11-05 | 2024-11-24 | 2024-11-26 |  |  |  | GD | 223264.55 | 10 | 18 | 19 | 2 | 49
CNSHA0001435236 | PENDING | ETA SIN 17 NOV | [8 empty] | DE | 86893.62
CNSHA0001435238 | PENDING | ETA SIN 17 NOV | [8 empty] | DE | 105073.56
CNSHA0001436863 | PENDING | ETA SIN 24 NOV | [8 empty] | DE | 100666.54
CNSHA0001436870 | MSMU2068290 | ETA SIN 24 NOV | 2024-10-25 | 2024-10-28 | 2024-11-21 | 2024-12-05 | 2024-12-07 |  |  |  | GD | 195349.65 | 3 | 24 | 14 | 2 | 43
CNSHA0001438092 | MEDU6264528 | ETA SIN 08 DEC | [8 empty] | DE
CNSHA0001438093 | BMOU2713893 | ETA SIN 08 DEC | [8 empty] | DE
CNSHA0001441155 | PENDING | ETA SIN 12 DEC | [8 empty] | DE
CNSHA0001441159 | TTNU 1081962 | ETA SIN 12 DEC | 2024-11-11 | 2024/11/11 | 2024-11-30 | 2024-12-11 |  |  |  |  | GD | 367314.42
CNSHA0001443594 | PENDING | ETA SIN 15 DEC | [8 empty] | DE
LCL commenced on
Wed 7/8/2024